## Sheet1
MAK (PR/R15) - Mr. Mohammad Nasser AL KAABI Villa-2, Qatar | [6 empty] | 3.65
Minutes of meeting MoM/MAK/01/02/2021
Variation order #2 - Revision 02 | 2021-02-14
This list represents the merger of client requests of 02/07/2020 (approved on 21/07/2020) and of 06/10/2020 (commented on 26/10/2020, and the last meeting on 01/02/2021 | [8 empty] | Lacasa
Particulars | Actual status | Date |  | Price (QRs.) | hours/sqm | rate |  | Total | 10% | Total
GF-02 Main entrance | ok | 2020-10-06 | GF-02 Main entrance 127 m² | 12747.625 | 127 | 91.25 | 25 | 11588.75 | 1158.875 | 12747.625
a. Requested revision of flooring design with new stone Solancis rosal real |  |  |  | 0 |  |  |  | 0 | 0 | 0
GF-03 Majlis | ok | 2020-10-06 | GF-03 Majlis 102 m² | 10238.25 | 102 | 91.25 | 25 | 9307.5 | 930.75 | 10238.25
a. Redesigning the GRG False ceiling from coffered to flat ceiling with decorative Robert Adams’ paint or plaster ornament |  |  |  | 0 |  |  |  | 0 | 0 | 0
b. Revisiting the design of the wooden library upwards |  |  |  | 0 |  |  |  | 0 | 0 | 0
GF-10, GF-11 Master bedroom to Swimming pool sitting |  |  |  | 0 |  |  |  | 0 | 0 | 0
a. Redesigning the area from Bedroom to Sitting room with Pantry and Closet, including Furniture layout, and FF&E mood board | new | 2021-02-01 |  | 0 |  |  |  | 0 | 0 | 0
b. Wall and ceiling in Pine wood and French Oak Parquet flooring |  |  |  | 0 |  |  |  | 0 | 0 | 0
GF-12 Master bathroom |  |  |  | 0 |  |  |  | 0 | 0 | 0
a. Redesigning the area for shower enclosures and anti-slip marble flooring and marble walls and vanity top - Michaelangelo or White Carrara marble | new | 2021-02-01 |  | 0 |  |  |  | 0 | 0 | 0
GF-15 Guest toilet |  |  |  | 0 |  |  |  | 0 | 0 | 0
a. Calacatta Oro marble wall cladding and vanity top, with Solancis stone flooring | new | 2021-02-01 |  | 0 |  |  |  | 0 | 0 | 0
b. Vanity cabinet in Patinated Beige painted wood |  |  |  | 0 |  |  |  | 0 | 0 | 0
GF-16 Wash area |  |  |  | 0 |  |  |  | 0 | 0 | 0
a. Calacatta Oro marble wall cladding with Solancis stone flooring | new | 2021-02-01 |  | 0 |  |  |  | 0 | 0 | 0
Vanity cabinet in Patinated Beige painted wood and Calacatta Oro top |  |  |  | 0 |  |  |  | 0 | 0 | 0
GF-17 Kitchen |  |  | GF-17 Kitchen 60 m² | 24090 | 60 | 365 | 100 | 21900 | 2190 | 24090
a. Full design development according to the Client requirements and photos |  | 2021-02-01 |  | 0 |  |  |  | 0 | 0 | 0
b. Requested design development on 06/10/2020 including photos of the required style | ok |  |  | 0 |  |  |  | 0 | 0 | 0
PDF drawing received from Mr. Alkaabi on 02/02/2021 for the new kitchen layout with relocation of windows to be considered |  |  |  | 0 |  |  |  | 0 | 0 | 0
Include cabinet for brooms and household cleaning products |  |  |  | 0 |  |  |  | 0 | 0 | 0
GF-18 Hallway | new |  | GF-18 Hallway 48 m² | 4818 | 48 | 91.25 | 25 | 4380 | 438 | 4818
a. Revision of flooring design with new stone + Emperador scuro |  | 2020-10-06 |  | 0 |  |  |  | 0 | 0 | 0
SUBMITTED on 22/07/2020 CGI 3D-Visual (2proposals) |  |  |  | 0 |  |  |  | 0 | 0 | 0
b. Requested design development on 06/10/2020 for flooring with Solancis rosal real tiles and filling, and 5 rows of Nero assoluto diamonds | done |  |  | 0 |  |  |  | 0 | 0 | 0
GF-19 Cloackroom to Powder room | new |  |  | 0 |  |  |  | 0 | 0 | 0
a. Redesigning by integrating a dressing table, mirror and chair | ok | 2020-10-06 |  | 0 |  |  |  | 0 | 0 | 0
b. Calacatta Oro marble wall cladding and vanity top, with Solancis stone flooring |  |  |  | 0 |  |  |  | 0 | 0 | 0
GF-20 Small majlis |  |  |  | 0 |  |  |  | 0 | 0 | 0
a. Replace Marble flooring by wall-to-wall hand tufted carpet | new | 2020-10-06 |  | 0 |  |  |  | 0 | 0 | 0
b. Design for Hand tufted carpet |  |  |  | 0 |  |  |  | 0 | 0 | 0
Redesign GRG false ceiling corniche same as BF-01 |  |  |  | 0 |  |  |  | 0 | 0 | 0
FF-02 Living room |  |  | FF-02 Living room | 0 |  |  |  | 0 | 0 | 0
a. No change of function to this area | ok | 2020-10-06 |  | 0 |  |  |  | 0 | 0 | 0
Redesign New double French door between existing columns |  |  |  | 0 |  |  |  | 0 | 0 | 0
FF-07 Office to Living room |  |  | FF-07 Office to Living room 32 m² | 12848 | 32 | 365 | 100 | 11680 | 1168 | 12848
a. Redesigning with specifications into Living room similar to GF-08 @ Villa-1 |  | 2020-10-06 |  | 0 |  |  |  | 0 | 0 | 0
No change of function to this area (06/10/2020) |  |  |  | 0 |  |  |  | 0 | 0 | 0
FF-12 Master bathroom | cancelled |  | FF-12 Master bathroom 14,30 m² | 2870.725 | 14.3 | 182.5 | 50 | 2609.75 | 260.975 | 2870.725
a. Requested design development for flooring and wall cladding in Calacatta Oro marble | new | 2020-10-06 |  | 0 |  |  |  | 0 | 0 | 0
Vanity cabinet in Patinated Beige painted wood and Calacatta Oro top |  |  |  | 0 |  |  |  | 0 | 0 | 0
Replace existing door by French Door with pleated sheer |  |  |  | 0 |  |  |  | 0 | 0 | 0
FF-15 Family living to Library/Office |  |  | FF-15 Family living to Library/Office 45 m² | 18067.5 | 45 | 365 | 100 | 16425 | 1642.5 | 18067.5
b. Redesigning the overall similar to FF-04 @ villa-1 in French oak and integrating Desk, desk chair, etc. |  | 2020-10-06 |  | 0 |  |  |  | 0 | 0 | 0
BF-01 Main Hall | ok |  | This is for the additional CGI 3D-visual for the marble variations | 0 |  |  |  | 0 | 0 | 0
a. Revision of flooring design with new stone + Bardiglio & Giallo Reale |  | 2020-10-06 | BF-01 Main Hall 70 m² | 0 |  |  |  | 0 | 0 | 0
b. Submittal of CGI 3D-Visual (2 views) |  |  |  | 0 |  |  |  | 0 | 0 | 0
c. NB: several rendering were submitted following the Client requests |  |  |  | 0 |  |  |  | 0 | 0 | 0
SUBMITTED on 23/07/2020 - 2 Nos.marble types options / 4 boards |  |  |  | 0 |  |  |  | 0 | 0 | 0
d. Requested design revision on 06/10/2020 for flooring with Baydaa al jazeera honed finish tiles and filling, and Nero assoluto diamonds | done |  |  | 0 |  |  |  | 0 | 0 | 0
BF-03 Toilet | new |  |  | 0 |  |  |  | 0 | 0 | 0
a. Requested design development on 06/10/2020 for flooring, vanity and elevation at toilet with Baydaa al jazeera honed finish tiles and filling, and Nero assoluto diamonds | new | 2020-10-06 |  | 0 |  |  |  | 0 | 0 | 0
BF-06 Pantry |  |  |  | 0 |  |  |  | 0 | 0 | 0
a. Requested design development on 06/10/2020 for flooring, ceiling, vanity and elevation after cancelling the folding door at pantrywith Baydaa al jazeera honed finish tiles and filling, and Nero assoluto diamonds | new | 2020-10-06 |  | 0 |  |  |  | 0 | 0 | 0
BF-09 Lobby, BF-11 Barber, BF-12 Massage, and BF-13 Toilet, Wash area and Showers |  |  |  | 0 |  |  |  | 0 | 0 | 0
a. Requested design development for flooring, vanity and elevation using Solancis rosal real flooring and Statuario marble vanity top, as well as proposal for framed statuario with Solancis. | new | 2020-10-06 |  | 0 |  |  |  | 0 | 0 | 0
BF-10 Gym |  |  |  | 0 |  |  |  | 0 | 0 | 0
a. Replace approved Vinyl flooring by special wood flooring to gym, french door, and mirror cladding + floor layout, elevations, and SMDS | new | 2020-10-06 |  | 0 |  |  |  | 0 | 0 | 0
b. Client to clarify + photos |  |  |  | 0 |  |  |  | 0 | 0 | 0
Aluwood windows |  |  |  | 0 |  |  |  | 0 | 0 | 0
a. Requested the replacement of existing aluminum windows by aluwood system (Aluminium outside and Wood inside) | new | 2020-10-06 |  | 0 |  |  |  | 0 | 0 | 0
Design, specifications and schedules |  |  |  | 0 |  |  |  | 0 | 0 | 0
Majlis building Main entrance door |  |  |  | 0 |  |  |  | 0 | 0 | 0
a. Replacing mid-panel by glass/stained glass | cancelled | 2020-10-06 |  | 0 |  |  |  | 0 | 0 | 0
b. Requested design on 06/10/2020 for ironwork gate with glass |  |  |  | 0 |  |  |  | 0 | 0 | 0
Need as-built drawings fron the site |  |  |  | 0 |  |  |  | 0 | 0 | 0
SPA Area: |  |  |  | 0 |  |  |  | 0 | 0 | 0
a. Doors to have a glass impost if enough false ceiling height |  |  |  | 0 |  |  |  | 0 | 0 | 0
b. Flooring in large porcelain tiles |  |  |  | 0 |  |  |  | 0 | 0 | 0
c. Built-in cabinet and Vanity counter at Beauty salon, massage, and manicure pedicure |  |  |  | 0 |  |  |  | 0 | 0 | 0
d. Beauty salon dressing chirs 2 chairs |  |  |  | 0 |  |  |  | 0 | 0 | 0
e. Manicure Pedicure station x2 |  |  |  | 0 |  |  |  | 0 | 0 | 0
f. Massage |  |  |  | 0 |  |  |  | 0 | 0 | 0
g. Store with sliding door and storage shelvings |  |  |  | 0 |  |  |  | 0 | 0 | 0
BF-11a Jacuzzi | new | 2021-02-01 |  | 0 |  |  |  | 0 | 0 | 0
Jacuzzi tub with ice machine |  |  |  | 0 |  |  |  | 0 | 0 | 0
Moroccan steam / hammam | new | 2021-02-01 |  | 0 |  |  |  | 0 | 0 | 0
Mosaic walls with antislip bamboo flooring or mosaic and built-in mosaic +bench |  |  |  | 0 |  |  |  | 0 | 0 | 0
Mr Alkaabi requested a new design proposal for the property gate and fence | new | 2021-02-01 |  | 0 |  |  |  | 0 | 0 | 0

## VO#2_Rev,02 Offer
MAK (PR/R15) - Mr. Mohammad Nasser AL KAABI Villa-2, Qatar
Minutes of meeting MoM/MAK/01/02/2021
|  | Variation Order #2 - Revision 02 approved on 21/06/2021 |  |  | 2021-06-22
NOTE: JMN shall provide the design concept to-scale on ACAD + design requirements and specifications MAC shall organize the dwgs with measurments and title block, etc., and complete design development for submittal
|  |  | CONTROL SHEET | Client |  | 2021-06-23 |  |  |  |  | Drawings revision of existing |  |  |  | Completed Drawing List
Area data (+/-) |  | s/n | Particulars | Status | Date | Existing Dwgs | JMN | Date | MAC | Date | Floor | Ceiling | Elev. | Details | Drawing Numbers
127 | GF02 | 1. | GF-02 Main entrance | New | 2020-10-06 | yes | design completed |  | Layout |  | 1 |  |  | 1 | Partition Plan, Floor Finish, and Marble Detail: ID-GF-02-001
a. Requested revision of flooring design with new stone Solancis rosal real
102 | GF03 | 2. | GF-03 Majlis | New | 2020-10-06 | yes | on going |  | Layout + Elev |  | 1 | 1 | 1 | 1
a. Redesigning the GRG False ceiling from coffered to flat ceiling with decorative Robert Adams’ paint or plaster ornament
b. Revisiting the design of the wooden library upwards
53.74 | GF10 | 3. | GF-10 Master bedroom to Swimming pool sitting | New | 2021-02-01 | no | design completed |  | Layout + Elev |  | 1 | 1 | 1 | 1 | Partition Plan: ID-GF-10-001 Ceiling Plan: ID-GF-10-004 Floor Finish Plan: ID-GF-10-005 Elevations: ID-GF-10-006/007/008 Details: ID-GF-10-009
a. Redesigning the area from Bedroom to Sitting room with Pantry and Closet, including Furniture layout, and FF&E mood board
b. Wall and ceiling in Pine wood and French Oak Parquet flooring
18.1 | GF11 | 3. | GF-11 Master bedroom Closet to Swimming pool sitting Pantery/Closet | New | 2021-02-01 | no | design completed |  | Layout + Elev |  | 1 | 1 | 1 | 1
a. Redesigning the area from Bedroom to Sitting room with Pantry and Closet, including Furniture layout, and FF&E mood board
b. Wall and ceiling in Pine wood and French Oak Parquet flooring
15.3 | GF12 | 4. | GF-12 Master bathroom | New | 2021-02-01 | no | design completed |  | Layout + Elev |  | 1 | 1 | 1 | 1
a. Redesigning the area for shower enclosures and anti-slip marble flooring and marble walls and vanity top –
b. Michaelangelo or White Carrara marble
5.7 | GF15 | 5. | GF-15 Guest toilet | New | 2021-02-01 | yes |  |  | Layout + Elev |  | 1 |  | 1 | 1
a. Calacatta Oro marble wall cladding and vanity top, with Solancis stone flooring
b. Vanity cabinet in Patinated Beige painted wood
8.64 | GF16 | 6. | GF-16 Wash area | New | 2021-02-01 | yes |  |  | Layout + Elev |  | 1 |  | 1 | 1 | Tile, Ceiling, and Layout Plan: ID-GF-16-001 Elevations (A-D): ID-GF-16-002 Details: ID-GF-16-003
a. Calacatta Oro marble wall cladding with Solancis stone flooring
b. Vanity cabinet in Patinated Beige painted wood and Calacatta Oro top
47.04 | GF17 | 7. | GF-17 Kitchen | New | 2021-02-01 | no |  |  | Layout + Elev |  | 1 | 1 | 1 | 1
a. Full design development according to the Client requirements and handed photos
b. Requested design development on 06/10/2020 including photos of the required style
c. PDF drawing received from Mr. Alkaabi on 02/02/2021 for the new kitchen layout with relocation of windows to be considered
d. To include cabinet for brooms and household cleaning products
48.2 | GF18 | 8. | GF-18 Hallway | Done | 2020-07-22 | [9 empty] | Tile Layout and Floor Plan: ID-GF-18-001
a. Revision of flooring design with new stone + Emperador scuro
SUBMITTED on 22/07/2020 CGI 3D-Visual (2proposals)
|  |  | b. Requested design development on 06/10/2020 for flooring with Solancis rosal real tiles and filling, and 5 rows of Nero assoluto diamonds | New | 2020-10-06 | yes | design completed |  | Layout |  | 1
4.32 | GF19 | 9. | GF-19 Cloackroom to Powder room | New | 2020-10-06 | yes | design completed |  | Layout + Elev |  | 1 | 1 | 1 | 1 | Layout, Tile, Ceiling Plan: ID-GF-19-001 Elevations (A-D): ID-GF-19-002 Details: ID-GF-19-003
a. Redesigning by integrating a dressing table, mirror and chair
|  |  | b. Calacatta Oro marble wall cladding and vanity top, with Solancis stone flooring | New | 2021-02-01
58.83 | GF20 | 10. | GF-20 Small majlis | New | 2020-10-06 | yes | on going |  | Layout |  | 1
a. Replace Marble flooring by wall-to-wall hand tufted carpet
b. Design for Hand tufted carpet
Redesign GRG false ceiling corniche same as BF-01
35.1 | FF02 | 11. | FF-02 Living room | New | 2020-10-06 | yes | design completed |  | Layout + Elev |  | 1 |  | 1 | 1 | Setting Out & Ceiling Plan: ID-FF-02-001 Tiling Layout. Furniture / Power Plan: ID-FF-02-002 Elevations: ID-FF-02-003 Door Details: ID-FF-02-004
a. No change of function to this area
b. Redesign New double French door between existing columns
31.3 | FF07 | 12. | FF-07 Office to Living room | Cancelled | 2020-10-06
a. Redesigning with specifications into Living room similar to GF-08 @ Villa-1
b. No change of function to this area (06/10/2020)
14.3 | FF12 | 13. | FF-12 Master bathroom | New | 2020-10-06 | yes |  |  | Layout + Elev |  | 1 |  | 1 | 1 | Partition Plan: ID-FF-12-001 Ceiling, Layout Plan: ID-FF-12-002 Elevations: ID-FF-12-003 Details: ID-FF-12-004
a. Requested design development for flooring and wall cladding in Calacatta Oro marble
b. Vanity cabinet in Patinated Beige painted wood & Calacatta Oro top
c. Replace existing door by French Door with pleated sheer
42.6 | FF15 | 14. | FF-15 Family living to Library/Office | New | 2020-10-06 | no |  |  | Layout + Elev |  | 1 | 1 | 1 | 1
Redesigning the overall similar to FF-04 @ villa-1 in French oak and integrating Desk, desk chair, etc.
69.43 | BF01 | 15. | BF-01 Main Hall | Done | 2020-07-23
a. Revision of flooring design with new stone + Bardiglio & Giallo Reale
b. Submittal of CGI 3D-Visual (2 views)
NB: several rendering were submitted following the Client requests
SUBMITTED on 23/07/2020 - 2 Nos.marble types options / 4 boards
|  |  | c. Requested design revision on 06/10/2020 for flooring with Baydaa al jazeera honed finish tiles and filling, and Nero assoluto diamonds | Done | 2020-10-06 | yes | design completed |  | Layout |  | 1
5.4 | BF03 | 16. | BF-03 Toilet | New | 2020-10-06 | yes |  |  | Layout + Elev |  | 1 | 1 | 1 | 1
Requested design development on 06/10/2020 for flooring, vanity and elevation at toilet with Baydaa al jazeera honed finish tiles and filling, and Nero assoluto diamonds
9.8 | BF06 | 17. | BF-06 Pantry | New | 2020-10-06 | yes |  |  | Layout + Elev |  | 1 | 1 | 1 | 1
Requested design development on 06/10/2020 for flooring, ceiling, vanity and elevation after cancelling the folding door at pantrywith Baydaa al jazeera honed finish tiles and filling, and Nero assoluto diamonds
40.74 | BF09+13+13a+13b | 18. | BF-09 Lobby, BF-13 Wash area, BF-13a Bathroom, and BF-13b Showers | New | 2020-10-06 | yes | on going |  | Layout + Elev |  | 1 | 1 | 1 | 1
Requested design development for flooring, vanity and elevation using Solancis rosal real flooring and Statuario marble vanity top, as well as proposal for framed statuario with Solancis.
96.81 | BF10 | 19. | BF-10 Gym | New | 2020-10-06 | yes | on going |  | Layout + Elev |  | 1 |  | 1 | 1
Replace approved Vinyl flooring by special wood flooring to gym, french door, and mirror cladding + floor layout, elevations, and SMDS
* Client to clarify + photos
6.42 | BF21+BF22 | 20. | BF-21 & BF-22 Lobby & Ice bathtub | New | 2021-02-01 | new | on going |  | Layout + Elev |  | 1 |  | 1 | 1
Jacuzzi tub with ice machine
42.42 | BF11+12+12a+12b | 21. | SPA Area : BF-11 Beaty salon, BF-12 Manicure pedicure, BF-12a Massage, and BF-12b Storage *Calliper needs as-built ACAD drawing for this revised area* | New | 2021-02-01 | yes | on going |  | Layout + Elev |  | 1 | 1 | 1 | 1
a. Doors to have a glass impost if enough false ceiling height
b. Flooring in large porcelain tiles
c. Built-in cabinet and Vanity counter at Beauty salon, massage, and manicure pedicure stations
d. Beauty salon dressing chirs 2 chairs
e. Manicure Pedicure station x2
f. Massage space with bed and shelving
g. Store with sliding door and storage shelvings
8.35 | BF23 | 22. | BF-23 Moroccan steam / Hammam | New | 2021-02-01 | new | on going |  | Layout + Elev |  | 1 | 1 | 1 | 1
Mosaic walls with antislip bamboo flooring or mosaic and built-in mosaic +bench
*Calliper to propose Moroccan Tadelakt plaster for walls
0 |  | 23. | Majlis building: Main entrance door | Cancelled | 2020-10-06
Replacing mid-panel by glass/stained glass
Requested design on 06/10/2020 for ironwork gate with glass
* Design concept submitted but cancelled
37.8 | GF05 | 24. | Majlis building: GF-05 Multipurpose room & GF-04 Private office | New | 2021-02-01
13.7 | GF04 |  | a. Requested Versailles wood flooring (parquet)
|  |  | b. Design drawing submitted in PDF on 10/02/2021 | Done | 2021-02-10 |  | submitted |  | none
0 |  | 25. | Mr. Mohamad Al-Kaabi requested a new design proposal for the property gate and fence | New | 2021-02-01 | need existing | on going |  | none
0 |  | 26. | Aluwood windows | New | 2020-10-06
Requested the replacement of existing aluminum windows by aluwood system (Aluminium outside and Wood inside)
* Design, specifications and schedules by others